## EMERG List
2014 EMERGENCY PRIORITY LIST - Facilities Committee
KEY: Black font = 2010 Priorities (Spring)
Green font = 2011 Priorities (Fall)
Red font = 2011 New Priorities (Spring)
Purple font = 2013 Priorities (Spring)
Blue Font = 2014 Priorities (Spring)
* Indicates Restated in Current Year APU's
Completed | In Process | NOT Completed | EMERGENCY Maintenance | 1 = Emergency
|  |  | Ventilation for rear of welding lab (WELD) | 1
|  |  | *Purchase and Install class D fire extinguishers in Chemistry labs A235B, A277, A279 (CHEM) | 1
|  |  | Resurface Breezeways & Infrastructure overhaul | 1
|  |  | Replace Balast in Entryway to A151-154 | 1
|  |  | Maintain, inspect, certify fume hoods & chem. storage (CHEM) | 1
|  |  | Repair or replace refrigeration in Cold rooms (BIOL) | 1
|  |  | Relocate gas cylinder shed storage doors & Widen cage door (WELD) | 1
|  | X | *Reinstall safety signs in Chemistry near eyewash/chemical shower stations in A277, A278, A279 (CHEM) | 1
|  |  | Repair gas leak A271 (ANTHR) | 1
|  | X | Repair/replace broken paper towel holders in A building (CHEM) | 1
|  |  | Stop leaking from above pipes (WELD) | 1
|  | X | *Repair/ replace safety shower curtain A278 (CHEM) | 1
|  |  | Dangerous floor/wall electrical outlets (MACH TECH) | 1
|  |  | Roof leaks over equipment rm. B120, B150, A192 (ECT) | 1
|  |  | Floor electrical access panels- danger of collapse (MACH TECH) | 1
|  | X | *Fix eyewash station drain vents - sewer vapors enter lab in A236 (CHEM) | 1
|  | X | *Ventilation efficiency check of flammable storage cabinets in A235B, A278, A279 (orig install faulty) (CHEM) | 1
|  |  | Repair women's ADA toilet - AC (ART) | 1
|  | X | *Replace old faucets and spigots in Chem labs A235, A236, A2767 and install backflow preventers where necessary (CHEM) | 1
|  |  | Repair leaking ceiling/roof (CARP) | 1
|  |  | Repair leaking thermostat (CARP) | 1
|  |  | Fix lights B210 so turn on reliably (BIOL) | 1
|  |  | Repair the inside stall doors in the women's Restroom in "E" Bldg (CUL) | 1
|  |  | Get Hot Water to Women's Restroom in "E" Bldg (CUL) | 1
|  |  | Locks on "E'" building doors are loose and need to be secured (CUL) | 1
|  |  | Replace Broken Mirror in Dance Studio D100 (DANCE) | 1
|  |  | B202 Door Lock repair - Inside remains in "open" position - door won't lock (BIO) | 1
|  |  | Student center tilting skillet needs to be moved to be brought up to code under a working hood (CUL) | 1
|  |  | Student center Stove top burners have clogged pilot lights and broken grates (CUL) | 1
|  |  | Bakery oven needs new gasket to prevent steam from leaking and burning students (CUL) | 1
| ? |  | Fix Water Leaks in Fitness Center Roof C102 (elec equip hazard) (KIN) | 1
|  |  | Welding: Repair fume extractor arms for 14 Booths for safe welding. And tensioners for stations 38 - 24. | 1
|  |  | Repair leaking ceilings in the welding lab, office and classroom (WELD) | 1