## LANEY
COLLEGE WORKSHEET - 2015-16 DEFERRED MAINTENANCE | [11 empty] | LANEY COLLEGE
• Please complete the columns highlighted in "yellow".
• Items can be added to the bottom of the list.
• Vent this list through your college process and return it to me so it can added to the master list in preparation for the 12/5/14 DFC meeting
(Due date: November 26, 2014)
Updated: 11/19/14
2015-16 DEFERRED MAINTENANCE LIST
Category | For Fiscal Year Ending | College Ranking Priority 1st, 2nd, 3rd etc. | College | Building /Area | Room | Type | Life & Safety Issue? | Description | Engineering Cost Estimates | Items Listed on the following DFC Document | DFC | Status DGS | Request Date (College) | Requestor (College) | COMMENTS
DM | 2015-16 | 1 | Laney | B120,B150,A153, A192 |  | roof/ceiling | YES | Roof leaks over equipment rm. B120, B150, A192, A153 |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 2 | Laney | WELD |  | roof/ceiling | YES | Repair leaking ceilings in the welding lab, office and classroom (WELD) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 3 | Laney |  |  | Plumbing | YES | Theater basement water intrusion | 20000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 4 | Laney | SC-Kitchen |  | Roofing | YES | Student center kitchen ceiling leaks (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 5 | Laney | E-Building |  | elevator | YES | E Bldg Elevator: Not Working. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 6 | Laney | Forum |  | Ceiling | YES | Ceiling Leak in Forum needs repair. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 7 | Laney | Theatre |  | elevator | YES | Theatre elevator is not working consistently. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 8 | Laney | C-Bldg. |  | plumbing | YES | Fitness Center water leak by window. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 9 | Laney |  | E/ET | Roof | YES | Roof leaks (E/ET) |  | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 10 | Laney | S/C |  | Appliance | YES | Replace food warmers | 16000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 11 | Laney | WELD |  | plumbing | YES | Stop leaking from above pipes (WELD) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 12 | Laney | Library |  | roof/ceiling | YES | roof leak from skylights replaced in summer 2014 |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 13 | Laney | Tower |  | Roof/Ceiling | YES | Ceiling Leak in T-850. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 14 | Laney | B103 |  | plumbing | YES | Corrosive liquid seeping from Chemistry lab to Cosmo classroom below. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2013 |  | DM
DM | 2015-16 | 15 | Laney | A-Buildng |  | plumbing | YES | Water drain is seeping sewage. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 16 | Laney | SC-Kitchen |  | electrical | YES | Student center tilting skillet needs to be moved to be brought up to code under a working hood (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 17 | Laney | A271 |  | plumbing | YES | Repair gas leak A271 (ANTHR) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2010 |  | DM
DM | 2015-16 | 18 | Laney | SC-Kitchen |  | electrical | YES | Bakery oven needs new gasket to prevent steam from leaking and burning students (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 19 | Laney | Biology |  | electrical | YES | Repair or replace refrigeration in Cold rooms (BIOL) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 20 | Laney | A151 & A154 |  | electrical | YES | Replace Balast in Entryway to A151-154 |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 21 | Laney | A235, A277 and A279 |  | Carpentry | YES | *Purchase and Install class D fire extinguishers in Chemistry labs A235B, A277, A279 (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 22 | Laney | A-Building |  | fire alarm | YES | Fire Alarm System needs sound adjustment so that all classrooms can hear it. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 23 | Laney | Student Center |  | electrical |  | Student Service Center basement and serving area equipment repairs needed. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 24 | Laney | A205 |  | plumbing |  | Water drain in RR is seeping water in ADA stall |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 25 | Laney | WELD |  | carpenter | YES | Relocate gas cylinder shed storage doors & Widen cage door (WELD) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | Work Order
DM | 2015-16 | 26 | Laney | WELD |  | HVAC | YES | Ventilation for rear of welding lab (WELD) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 27 | Laney | MACH TECH |  | flooring | YES | Dangerous floor/wall electrical outlets (MACH TECH) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 28 | Laney | CHEM |  | plumbing | YES | *Replace old faucets and spigots in Chem labs A235, A236, A2767 and install backflow preventers where necessary (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | Work Order
DM | 2015-16 | 29 | Laney | A235, A277 and A279 |  | HVAC | YES | *Ventilation efficiency check of flammable storage cabinets in A235B, A278, A279 (orig install faulty) (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 30 | Laney | CHEM |  | plumbing | YES | *Fix eyewash station drain vents - sewer vapors enter lab in A236 (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 31 | Laney | MACH TECH |  | electrical | YES | Floor electrical access panels- danger of collapse (MACH TECH) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 32 | Laney | Tower 3rd Floor |  | flooring |  | Trip hazard: Repair Stripping on door from 3rd floor stairwell by counseling (COUNC) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 33 | Laney | WELD |  | HVAC | YES | Welding: Repair fume extractor arms for 14 Booths for safe welding. And tensioners for stations 38 - 24. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 34 | Laney | WELD |  | HVAC | YES | Welding: Repair fume extractor arms for 14 Booths for safe welding. And tensioners for stations 38 - 24. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 35 | Laney |  | Mach Tech | Elect | YES | Dangerous floor/wall electrical outlets (MACH TECH) | 5800 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 36 | Laney | KIN |  | roof/ceiling | YES | Fix Water Leaks in Fitness Center Roof C102 (elec equip hazard) (KIN) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 37 | Laney | E-Building |  | plumbing | YES | Leaking toilet in women's restroom. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 38 | Laney | Library |  | plumbing | YES | Water leak in 3rd floor women's restroom. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 39 | Laney | B109 and B108 |  | plumbing | YES | Toilet water leaks in bathrooms. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 40 | Laney | E-Building |  | plumbing | YES | Upper E Bldg. Men's Restroom : Please repair leak. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 41 | Laney | SC-Kitchen |  | electrical | YES | Student center Stove top burners have clogged pilot lights and broken grates (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | Work Order
DM | 2015-16 | 42 | Laney | Art Center |  | HVAC | YES | No heating in classroom. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 43 | Laney | Art Center |  | plumbing | YES | Floor drain and pipes water backup and need cleaning. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 44 | Laney | A Bldg |  | Plumbing | YES | Repair drains above rooms A152, A154a & A152b (GRART) | 16000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 45 | Laney |  |  | Plumbing | YES | Replace sewer injection pumps | 60000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 46 | Laney | B109 |  | Plumbing | YES | Floor drain P trap is rotted out | 4500 |  | 2015
DM | 2015-16 | 47 | Laney | E Bldg |  | Kitchen | YES | Replace walk-in cooler | 45000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 48 | Laney | A-Building |  | HVAC | YES | Certify all chemical fume hoods in Building "A" |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 49 | Laney | Campus |  | Carpenter | YES | Several Bldgs. Handicap toilet stalls broken. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 50 | Laney | Library |  | flooring | YES | Carpet tripping hazard |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 51 | Laney | Library |  | flooring | YES | Trip hazard from loose carpet in Library south side stair. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 52 | Laney |  | B256 | HVAC | YES | HVAC system is noisy | 15000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 53 | Laney | D Bldg | D200 | HVAC | YES | HVAC system is noisy | 15000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 54 | Laney |  | Biology | HVAC | YES | Repair or replace refrigeration in Cold rooms (BIOL) | 22000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 55 | Laney | AC |  | plumbing | YES | Repair women's ADA toilet - AC (ART) |  | 2015-16 Deferred Maintenance | 2015 |  |  |  | DM
DM | 2015-16 | 56 | Laney | CARP |  | electrical | YES | Repair leaking thermostat (CARP) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 57 | Laney | E-CUL |  | plumbing | YES | Get Hot Water to Women's Restroom in "E" Bldg (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 58 | Laney | B210 |  | electrical | YES | Fix lights B210 so turn on reliably (BIOL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | Work Order
DM | 2015-16 | 59 | Laney | ARCH |  | flooring | YES | Repair loose vinyl floor tiles in lobby (ARCH) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 60 | Laney | GRART |  | plumbing | YES | Maintain floor drains to prevent fume release into classes (GRART) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 61 | Laney | G236 |  | flooring | YES | Repair floor tiles and install weather strip G236 (AET) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 62 | Laney | CALWORKS |  | ADA |  | Maintain facilities for safety, security, access for persons with disabilities (CALWORKS) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 63 | Laney | CHEM |  | Carpenter |  | * Install additional corrosive chemical storage cabinet A278 and install fume vent. (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 64 | Laney | A152, A154 & A152B |  | plumbing |  | Repair drains above rooms A152, A154a & A152b (GRART) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 65 | Laney | ART |  | plumbing |  | Repair or replace sinks’ clogged drains or valves in all studios in Art Center (ART) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 66 | Laney | A235 & A278 |  | plumbing |  | *Replace faulty dishwashers A235B and A278 (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 67 | Laney | Child Care |  | plumbing |  | REPAIR non-working toilets. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 68 | Laney | Forum |  | plumbing |  | Repair Leaking water fountains. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 69 | Laney | A-Building |  | plumbing |  | Water fountains not working in building A. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 70 | Laney | Library |  | plumbing |  | Women's RR : both sinks are not working. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 71 | Laney | Tower |  | plumbing |  | Water Pressure low -Tower building-restrooms and fountains. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 72 | Laney | Lockeroom |  | plumbing |  | Shower will not shut off in women's locker room. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 73 | Laney | Forum |  | plumbing |  | Forum - Men's Restroom: Urinal will not Flush. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 74 | Laney | B-Building |  | plumbing |  | Two Restroom sinks no running water. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 75 | Laney | Library |  | plumbing |  | Library 1st flr-Drinking fountain is not working. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 76 | Laney | Lockeroom |  | plumbing |  | Women's LockerRoom : Sink clogged. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 77 | Laney | Art Center |  | plumbing |  | leaking sink in Art Center needs repair. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 78 | Laney | Campus |  | plumbing |  | Finish replacing water fountains throughout campus (ASLC) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 79 | Laney | GRART |  | plumbing |  | Replace overhead drainpipes in ceilings (GRART) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 80 | Laney | SC-Kitchen |  | plumbing |  | Student Center has 4 sinks that need repair and Sandwich station (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 81 | Laney | BIO |  | plumbing |  | Fix leaky faucets in Biology labs, offices and prep room (BIO) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 82 | Laney | LIB |  | plumbing |  | Remove 2nd Floor Water Fountain in Library (LIB) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 83 | Laney | A235, A236 & A237 |  | plumbing |  | Repair plumbing - Fix all non-functioning water faucets and spigotsin A235, A236,A237 (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 84 | Laney | ECT |  | plumbing |  | Fix hand wash sink room B-150. (ECT) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 85 | Laney | Student Center |  | plumbing |  | Basement Kitchen urinal not functioning properly |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 86 | Laney | Gym |  | plumbing |  | One of the Men's RR G200B faucets doesnt work. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 87 | Laney | Library |  | plumbing |  | Urinal out of order and sinks not working -Men's 3rd/4th floor RR |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 88 | Laney | B153 |  | plumbing |  | B153, water will not shut off for the hand wash sinks. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 90 | Laney | GRART |  | security |  | Loss prevention measures (security cameras, window bars) (GRART) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 91 | Laney | Student Center |  | Window |  | Replace broken window in Student Center. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 92 | Laney | BIO |  | window |  | *Replace broken blinds in B207 (missed in renovation) (BIOL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 92 | Laney | MUSIC |  | window |  | Upgrade windows (MUSIC) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 93 | Laney | SC-Kitchen |  | Elect. |  | Repair the gaskets in the bakery kitchen freezer and refrigerator (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 94 | Laney | A-Building |  | windows |  | Replace broken windows. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 95 | Laney | A-Building |  | HVAC |  | HVAC not working properly. Check for repair. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 96 | Laney | A-153 |  | HVAC |  | No heating in classroom. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 97 | Laney | Campus |  | Floor |  | New floor for cadaver boxes | 12000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 98 | Laney | Tower |  | electrical |  | Electrical outlets not working in multiple buildings. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 99 | Laney |  |  | Elect |  | Electrical switch gear replacement - Phase I | 450000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 100 | Laney | A Bldg |  | HVAC |  | Air handler & coil replacements | 350000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 101 | Laney | E Bldg |  | HVAC |  | Replace two chiller barrel (thin walls) | 50000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 102 | Laney | Library |  | HVAC |  | VFD replacement x 2 | 8000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 103 | Laney | Pool |  | HVAC |  | Replace pool heaters - phase II | 350000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 104 | Laney | A Bldg |  | HVAC |  | Negative pressure - Phase II | 150000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 105 | Laney | Child Care |  | HVAC |  | Replace HVAC roof package units x5 (mfg 1999) | 145000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 106 | Laney | Child Care |  | HVAC |  | Replace restroom exhaust fans | 2200 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 10 | Laney | Pool |  | HVAC |  | Replace pool heaters - phase I | 175000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 108 | Laney | Campus |  | HVAC |  | Replace Delta coaxial to Cat-6 Upgrades | 3500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 109 | Laney | BIO |  | Carpenter |  | Fix ceiling in bio offices (BIOL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 110 | Laney | KIN |  | Carpenter |  | Replace pool deck, grout/sealers and grates over drains (KIN) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 111 | Laney | Tower |  | Carpenter |  | Repair concrete step, and bottom edge of building | 8500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 112 | Laney | B100 |  | electrical |  | Equipment not working instruction is hindered in COSMO. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 113 | Laney | E-Building |  | electrical |  | E--118 Main Bakery : Oven thermostat is not working. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 114 | Laney | E-Building |  | electrical |  | E Bldg Electrical lighting systems problems: |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 115 | Laney | Gym |  | electrical |  | Light sensor in GYM112 and GYM110 will not turn on. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 116 | Laney | BIO & CHEM |  | flooring |  | Replace/repair flooring where needed in Biology and Chemistry (BIOL, CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 117 | Laney | A-184 and A-185 |  | HVAC |  | HVAC needs repair. No heat and uncontrolled cold air. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 118 | Laney | C102 |  | HVAC |  | Building Fan broken and smoking in gym room. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 119 | Laney | AET |  | HVAC |  | Check/replace air handling equip filters in Architecture (AET) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2010 |  | DM
DM | 2015-16 | 120 | Laney | Campus |  | Doors |  | Secure locks all new smart classrooms campuswide (MUSIC,) |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2011 |  | DM
DM | 2015-16 | 121 | Laney | CHEM |  | Carpenter |  | Fix all broken laboratory drawers (broken/ missing handles) (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 122 | Laney | F202 |  | Carpenter |  | Replace/repair ceiling tiles F202 (BUS) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 123 | Laney | WELD |  | Elect. |  | Blow out electronics inside welding machines (WELD) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 124 | Laney | CHEM |  | Elect. |  | Replace all power outlets on student Chem workbenches with appropriate GFCI outlets in A235, A236, A277. (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 124 | Laney | WELD |  | Elect. |  | Revamp Manifold in Welding (WELD) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 126 | Laney | LIB |  | Elect. |  | Remove electrical poles and reroute wiring into ceiling in Library Teaching lab L-104 (LIB) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 127 | Laney | CARP |  | Elect. |  | Repair exterior canopy electrical outlets (CARP) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 128 | Laney | JOURN |  | Elect. |  | Power to unpowered electrical jack (JOURN) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 129 | Laney | G201 & 202A |  | flooring |  | Replace carpet in G201 & 202A (MATH) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 130 | Laney | CARP |  | HVAC |  | Replace insulation on cooling system G160 (CARP) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 131 | Laney | Campus |  | Carpenter |  | Replace broken/missing toilet paper/towel dispenser campuswide. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 132 | Laney | C-Bldg. |  | HVAC |  | Replace coils in condensing unit. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 133 | Laney | D-Bldg and Gym |  | HVAC |  | Clean condensing unit coil. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 134 | Laney | Theatre |  | flooring |  | Laney Tower Restroom - Floor needs to be regrout |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 135 | Laney | Student Center |  | Paint |  | Painting Request: Room 410, 412,402,401 A |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 136 | Laney | Theatre |  | Ceiling |  | Ceiling Tiles missing in office of Theatre. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 137 | Laney | E-CUL |  | plumbing | YES | Repair the inside stall doors in the women's Restroom in "E" Bldg (CUL) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 138 | Laney | campus |  | carpenter | YES | Locks across campus old, not working and need replacements |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | Work Order
DM | 2015-16 | 139 | Laney | A-Building |  | flooring |  | Linoleum flooring needs repair for tripping hazards. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 140 | Laney | B251 |  | Ceiling |  | Ceiling Panels need to be replaced in B251. |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 141 | Laney | S/C |  | Paint |  | Repair kitchen wall (ceramic tile and painting) | 5500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 142 | Laney | Eagle Village |  | Floor |  | Bathroom floor needs replacing (structural) | 6500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 143 | Laney |  | Pool | Carpentry |  | Replace pool deck grout and grates (KIN) | 4500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 144 | Laney | Theater |  | Carpentry |  | Replace ceiling tiles in dressing rooms (THEATER) | 3500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 145 | Laney | B Bldg | B150 | Elect |  | Change out entire existing elec. Outlet in B150- safety (ECT) | 6500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 146 | Laney | Theater |  | Elect |  | Theatre Electrical: Replace old raceways, circuits, and floor pockets; edison outlets; update stage manager's control panel (THEATER) | 24000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 147 | Laney | Theater |  | Elect |  | Replace Theatre dimmers (only 1/2 working) - can't be repaired (THEATER) | 8500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 148 | Laney | Library |  | Elect |  | Replace lights in Library atrium (LIB) & ARCH (G bldg) | 8500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 149 | Laney | Campus |  | Elect |  | *Repair/maintain all radio-controlled clocks in A bldg. and all buildings, offices and labs . (CHEM) | 14000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 150 | Laney | A Bldg | A235 | Elect |  | Replace all power outlets on student Chem workbenches with appropriate GFCI outlets in A235, A236, A277. (CHEM) | 7500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 151 | Laney |  | Mach Tech | Elect |  | Floor electrical access panels- danger of collapse (MACH TECH) | 2400 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 152 | Laney | Theater |  | Elect |  | Replace lighting and electrical systems in theatre (THEATER) | 25000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 153 | Laney | Walkways |  | Elect |  | Outdoor Lighting near driveway & estuary - AC | 12000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 154 | Laney |  |  | Elevator |  | Refurbish Library elevators from floor to ceiling (LIB) | 24000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 155 | Laney |  |  | Flooring |  | Replace/repair flooring where needed in Chemistry | 15000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 156 | Laney |  |  | Flooring |  | Replace the Gymnasium Floor - last layer, can not sand down (KIN) | 120000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 157 | Laney |  | Locker Rm | Flooring |  | Resurface Faculty Locker room Floors | 6500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 158 | Laney | A Bldg |  | Flooring |  | Replace/ Install Flooring in Chemistry Stockrooms A235B, A278, A279 (CHEM) | 9500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 159 | Laney |  | Biology | Flooring |  | Fix flooring in Biology Rooms - coming up creating trip hazard (BIO) | 18000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 160 | Laney |  | Weld | HVAC |  | Welding: Repair fume extractor arms for 14 Booths for safe welding. And tensioners for stations 38 - 24. | 7500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 161 | Laney |  |  | Locksmith |  | Secure locks all new smart classrooms campus wide (MUSIC,) | 11200 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 162 | Laney |  | D100 | Paint |  | Paint D100 (DANCE) | 5000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 163 | Laney |  | Art | Plumbing |  | Repair or replace sinks’ clogged drains or valves in all studios in Art Center (ART) (need clarifiers added) | 12000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 165 | Laney |  |  | Plumbing |  | Replacing water fountains - phase II | 24000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 166 | Laney | CHEm |  | Doors |  | Repair Door to A277A - Hinge is bent and doesn't close properly (CHEM) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 167 | Laney | L-102 & L101 |  | Doors |  | Install Dutch door between L102 and L101 (LIB) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2011 |  | DM
DM | 2015-16 | 168 | Laney | CARP |  | Doors |  | Replace front door G160 (CARP) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2014 |  | DM
DM | 2015-16 | 169 | Laney | TASC |  | Paint |  | Repair and paint damaged walls (TASC) |  | 2015-16 Deferred Maintenance | 2015 |  | Spring 2013 |  | DM
DM | 2015-16 | 170 | Laney |  |  | Paint |  | Painting - Phase I | 80000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 171 | Laney | Tower |  | elevator |  | Elevator #2 - 9th floor key control not working. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 172 | Laney | Art Center |  | Paint |  | Graffati on walls in restrooms needs to be painted. |  | 2015-16 Deferred Maintenance | 2015 |  | Fall 2014 |  | DM
DM | 2015-16 | 173 | Laney |  | G160 | Carpentry |  | Replace front door G160 (CARP) | 2000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 174 | Laney |  | G201 | Flooring |  | Replace carpet in G201 | 8500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 175 | Laney |  | A202 | Flooring |  | Replace carpet in 202A | 8500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 176 | Laney |  | TASC | Paint |  | Repair and paint damaged walls (TASC) | 6500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 177 | Laney | Library |  | Paint |  | Paint interior walls (LIB) | 42000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 178 | Laney |  | Locker Rm | Paint |  | Paint walls in Faculty Locker room (KIN) | 2200 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 179 | Laney | [6 empty] | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 180 | Laney | Tower |  | Flooring |  | Replace Health center carpet | 12000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 181 | Laney | Campus |  | Carpenter |  | Repair sidewalks along canal | 35000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 182 | Laney | Campus |  | Elect. |  | Repair sidewalk lighting along the canal | 15000 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 183 | Laney | Athletics |  | Elect. |  | Repair walkway lights near batting cage after wire theft | 4500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 184 | Laney | Tennis |  | Elect. |  | Repair tennis court lights x2, 20 to 30 amp breaker, christy box, power to one light after camera stole circuit, momentary switch, theft | 7500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 185 | Laney | Campus |  | Carpenter |  | Repair hand rails around campus | 6500 | 2015-16 Deferred Maintenance | 2015
DM | 2015-16 | 186 | Laney | A |  | Doors |  | Door swings the wrong direction - MRR |  | Privacy concern | 2015