## Sheet1
Status Date: Costs and Funding as of Current Month
Status Date: Costs and Funding as of September 30, 2024
Bond Spending Plan
|  |  | Proj # |  |  | Type 1 | 6/30/20 Total Project Cost Estimate | 7/31/21 Total Project Cost Estimate 2 |  | 2024-09-30 | [13 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
|  | Old Proj # |  | DCA | CM/PM |  |  |  | 9/30/24 Total Project Cost Estimate | Construction Budget | Contingency Budget Remaining (% against Construction Budget) | [6 empty] | Phase 1 | Phase 2 | 9/30/24 Measure G | 9/30/24 State Match | 9/30/24 Measure A | 9/30/24 Federal | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
[11 empty] | CC |  | DC |  | OC |  | Total Contingency
College of Alameda
| New Center for Liberal Arts - DB |  | 2361 | no | Complete | New | 500000 | 13757811 | 11365020.89 | 7391514 | [7 empty] | 11365020.89 |  | 0 |  | 11365020.89 | bar: 2020 Q1 to 2020 Q3
| Auto and Diesel Technologies - DBB |  | 2404 | yes | SZ | New | 37517566 | 37517566 | 40808906.11 | 31632400 | 1403232 | 4.436% |  |  | 87050 | 0.2752% | 1490282 | 40808906.11 |  | 9926140 | 16569000 | 14313766.11 | bar: 2020 Q2 to 2025 Q2
| Aviation Complex Hangar B Phase 1 - DBB |  | 2365 | yes | JF/EM | Mod | 7464494 | 7464494 | 12650944 | 8986450 | 330000 | 3.672% |  |  | 520804 | 5.795% | 850804 | 12650944 |  | 11551504 |  | 1099440 | bar: 2020 Q3 to 2026 Q2
| Aviation Complex Hangar A Phase 2 - DBB |  | 2406 | yes | JF/EM | New | 31133686 | 31133686 | 41053642 | 31495778 | 1737291 | 5.516% | 448822 | 1.425% | 807957 | 2.565% | 2994070 | 41053642 |  | 27952688 | 12242000 | 858954 | bar: 2022 Q3 to 2027 Q4
| New Science/Admin Bldg - DB |  | 2491 | no | on hold | New | 97131138 | 97131138 | 84394247 | 56179292 | 5408638 | 9.627% | 5508637.5 | 9.805% | 2754319 | 4.903% | 13671594.5 |  | 84394247 | 84394247 | bar: 2025 Q3 to 2029 Q3
| Campus Wide Modernization |  | 2504 |  |  |  | 0 |  | 6277362 | 6277362 | [7 empty] | 6277362 |  | 6277362 | bar: 2024 Q3 to 2026 Q4
| Campus Mod - Keyless Entry |  | 2504-01 |  |  |  | 0 |  | 76252 | [8 empty] | 76252 |  | 76252
| Swing Space (Science in C&D) - DBB |  |  |  |  | Mod | bar: 2020 Q3 to 2022 Q1
| Science Annex Upgrades - DBB (Previous Swing) |  | 2491-01 | yes |  | Mod | 5005625 | 5005625
| Library Renovation (On Hold - FPP Score 138) |  | 2405 |  |  | Mod
| Building F Modernization (On-Hold Student Ctr) |  | 2494 |  |  | Mod
[12 empty] | #DIV/0! | [5 empty] | 0 | bar: 2021 Q1 to 2022 Q4
| Demo Diesel Bldg - (Included in Auto/Diesel) |  | 2404 |  |  | Mod | 1122001 | 1122001
| Science Annex- HVAC/ 860 Atlantic HVAC Upgrades*** |  | 2408 | yes | Complete | Mod | 0 | 142374 | 237836 | 107953 | [7 empty] | 237836 |  | 24168 |  | 213668
| College- Unallocated |  | 2420 |  |  |  | 0 |  | 9770895 | 9744925 | [7 empty] | 9770895 |  | 9770895
| College- Unallocated - designated for future CM contract |  | 2420 | [5 empty] | 1407734 | [8 empty] | 1407734 |  | 1407734
| Infrastructure |  | 2398 |  |  |  | 12912691 | 12912691
| Infrastructure – Unallocated |  | " |  |  | Mod |  |  | 1712186 | 1712186 | [7 empty] | 1712186 |  | 1712186
| Infrastructure- CM Fees |  | " | [5 empty] | 1184316 | [8 empty] | 1184316 |  | 1184316
| Elevator Upgrades |  | 2398-03 | yes | BC | Mod | 0 |  | 1424212 | 1221054 | 122106 | 10% |  |  | 61053 | 5% | 183159 | 1424212 |  | 1424212
| Roofing Repairs and Replacement |  | 2398-04 | yes | on hold | Mod | 0 |  | 1019496 | 833233 | 43802 | 5.257% |  |  | 122462 | 14.7% | 166264 | 1019496 |  | 1019496
| Aviation Sewer Pump Replacement/Lift Station |  | 2398-05 | yes | HPLE | Mod | 0 |  | 346867 | 326752 | 7969 | 2.439% |  |  | 8146 | 2.493% | 16115 | 346867 |  | 346867
| Pothole Repairs at Main Roads |  | 2398-07 | yes | Complete | Mod | 0 |  | 27353 | 27353 | [7 empty] | 27353 |  | 27353
| BMS Upgrades |  | 2398-08 | yes | Complete | Mod | 0 |  | 40581 | 40581 | [7 empty] | 40581 |  | 40581
| Building L Lighting Contactor Replacement |  | 2398-09 | yes | Complete | Mod | 0 |  | 32336 | 32336 | [7 empty] | 32336 |  | 32336
| Plumbing C-103 Sink Repair |  | 2398-10 | yes | Complete | Mod | 0 |  | 7900 | 7900 | [7 empty] | 7900 |  | 7900
| Aviation Sign Repair |  | 2398-11 | yes | Complete | Mod | 0 |  | 5500 | [8 empty] | 5500 |  | 5500
| Fields - Tennis Courts |  | 2398.12 | [14 empty] | 0
| Fields - Soccer |  | 2398.13 | [14 empty] | 0
| ADA Upgrades, Bdg D Restroom Modernization |  | 2398-24 | yes | SZ | Mod | 0 |  | 2540839 | 1676173 | 167617 | 10% |  |  | 79662 | 4.753% | 247279 | 2540839 |  | 2540839
| H Building Landscape Irrigation |  | 2398.14 | yes | Complete
| Alameda Bleacher Install |  | 2490 | no | Complete | Mod | 0 | 246192 | 246290 | [8 empty] | 246290 |  |  |  | 246290
| COA- FF&E |  | 2410-01 | no | Complete | Mod | 0 |  | 60236 | [8 empty] | 60236 |  |  |  | 60236
| Information Technology |  | 2411 | no |  | IT | 2850000 | 2850000 | 2850001 | [8 empty] | 1425000.5 | 1425000.5 | 2737223 |  | 112778
| Library Equipment and Books (based on 2022 adopted BAM) |  | 2378-02 | no
| College of Alameda Subtotal | [5 empty] | 195637201 | 209283578 | 219540952 | 157693242 | 9220655 |  | 5957459.5 |  | 4441453 |  | 19619567.5 | 133721704.5 | 85819247.5 | 162459799 | 28811000 | 28270153
Berkeley City College
| 2118 Milvia Street (New Building) - DB |  | 2477 | yes | CH | New | 83851707 | 83851707 | 101158304 | 79508579 |  |  |  |  | 5226173 | 6.573% | 5226173 | 101158304 |  | 91931680 |  | 9226624 | bar: 2020 Q3 to 2026 Q2
0 | bar: 2023 Q2 to 2026 Q3
| 2050 Center Reconfiguration - DB |  | 2496 | no | CH | Mod | 31550808 | 31550808 | 14579825.8854 | 6569876 | 1662000 | 25.3% | 1586203 | 24.14% | 831000 | 12.65% | 4079203 |  | 14579825.8854 | 14579825.8854 | bar: 2025 Q2 to 2028 Q3
| Campus Wide Modernization |  | 2505 |  | BC |  | 0 |  | 72528 | 72528 | [7 empty] | 72528 |  | 72528
| Campus Mod - Keyless Entry |  | 2505-01 | no | BC |  | 0 |  | 30501 | [8 empty] | 30501 |  | 30501
| College- Unallocated |  | 2520 |  |  |  | 0 |  | 1919885 | 1234349 | [7 empty] | 1919885 |  | 1898714 |  | 21171
| Infrastructure |  | 2497 |  |  |  | 3000000 | 3000000
| Infrastructure – Unallocated |  | " |  |  | Mod | 0 |  | 781433 | 781433 | [7 empty] | 781433 |  | 781433
| Infrastructure- CM Fees |  | " |  |  |  | 0 |  | 408240 | [8 empty] | 408240 |  | 408240
| Entry Door Replacement |  | 2497-01 | yes | CH | Mod | 0 |  | 339160 | 183000 | 14060 | 7.683% |  |  |  |  | 14060 | 339160 |  | 339160
| Roof Maintenance and Repair |  | 2497-02 | yes | Complete | Mod | 0 |  | 26915 | 26915 | [7 empty] | 26915 |  | 26915
| Bundle 1a-1d HVAC Controls Investigation System Assessment |  | 2497-03 | yes | Complete | Mod | 0 |  | 14775 | 14775 | [7 empty] | 14775 |  | 14775
| Elevators |  | 2497-04 | yes | BC | Mod | 0 |  | 211890 | 211890 | [7 empty] | 211890 |  | 211890
| Janitorial Sinks Modernization |  | 2497-05 | yes | CH | Mod | 0 |  | 34470 | 30600 | [7 empty] | 34470 |  | 34470
| Bundle 4a-4b HVAC Cooling Tower and BDD Equip Assessment |  | 2497-06 | yes | Complete | Mod | 0 |  | 52423 | 52423 | [7 empty] | 52423 |  | 52423
| Student Lounge Window Shades |  | 2497-08 | yes | Complete | Mod | 0 |  | 3680 | 3680 | [7 empty] | 3680 |  | 3680
| Room 125 |  | 2497-09 | no |  |  |  |  | 23985 | 23985 | [7 empty] | 23985 |  | 23985
| Berkeley ADA Modernization |  | 2323 | no | Complete | Mod | 0 | 748941 | 354450 | 231694 | [7 empty] | 354450 |  |  |  | 354450
| Information Technology |  | 2412 | no |  | IT | 2850000 | 2850000 | 2850000.105 | [8 empty] | 1425000.0525 | 1425000.0525 | 2850000.105
| Library Equipment and Books (based on 2022 adopted BAM) |  | 2378-08 | no |  |  | 0
| Berkeley College Subtotal | [5 empty] | 121252515 | 122001456 | 122862464.9904 | 88945727 | 1676060 |  | 1586203 |  | 6057173 |  | 9319436 | 106857639.0525 | 16004825.9379 | 113260219.9904 |  | 9602245
Laney College
| Portable Modular Village - DBB |  | 2336 | yes | AG | New | 2739820 | 2739820 | 4464449 | 1794103 | [7 empty] | 4464449 |  | 4285246 |  | 179203 | bar: 2020 Q2 to 2022 Q3
| Laney Locker Room Modernization - DB |  | 2475 | yes | BK/AG | Mod | 10974270 | 10974270 | 11498832 | 8550000 | 47337 | 0.5536% |  |  | 303037 | 3.544% | 350374.0055 | 11498832 |  | 9863803 |  | 1635029 | bar: 2020 Q3 to 2026 Q2
| EBMUD Water Main Relocation - DBB |  | 2492 | yes | SD | New | 2001383 | 2001383 | 3108005 | 1906528 | 158172 | 8.296% |  |  | 187700 | 9.845% | 345872.083 | 3108005 |  | 3108005 | bar: 2021 Q1 to 2024 Q3
| Central Plant / Cooling Tower - DB |  | 2493 | yes | LR/SD | Mod | 16504490 | 16504490 | 20284686 | 16286183 |  | 0% |  |  | 252960 | 1.553% | 252960 | 20284686 |  | 17066984 |  | 3217702 | bar: 2020 Q3 to 2025 Q3
| Learning and Resource Center - DBB |  | 2383 | yes | AW | New | 95740418 | 95740418 | 113881042 | 88288256 | 8811355 | 9.98% |  |  | 3554819 | 4.026% | 12366174.0998 | 113881042 |  | 79835941 | 24417000 | 9628101 | bar: 2020 Q1 to 2027 Q1
| Laney Theater Modernization - DBB |  | 2481 | yes | SD | Mod | 28796531 | 28796531 | 39184943 | 30000000 | 3000000 | 10% |  |  | 798886 | 2.663% | 3798886.1 | 39184943 |  | 30805045 | 7999000 | 380898 | bar: 2020 Q2 to 2024 Q4; 2025 Q2 to 2026 Q4
0
| Student Center and Culinary Arts - DBB |  | 2498 |  |  | Mod | 19868812 | 19868812 | [9 empty] | 0 |  | 0
| Campus Wide Modernization |  | 2506 |  |  |  | 0 |  | 4648860 | 4648860 | [7 empty] | 4648860 |  | 4648860
| Campus Wide Mod - Keyless Entry |  | 2506-01 |  | BC |  | 0 |  | 106753 | [8 empty] | 106753 |  | 106753
| Campus Wide Mod - Fire Alarm System Mod |  | 2506-02 | yes | AM |  | 0 |  | 13267990 | 9800000 | 980000 | 10% | 980000 | 10% | 490000 | 5% | 2450000.2 | 13267990 |  | 13267990
|  |  |  | yes | [15 empty] | 0
| Student Welcome Center (Lib Mod) - DBB |  | 2318 | no |  | Mod | 30169485 | 30169485
0 | bar: 2023 Q3 to 2028 Q4
| STEM Building (Phase 1) - DB |  | 2462 | no |  | New | 150680899 | 150680899 | 79084097 | 43012497 | 7821000 | 18.18% | 7821000 | 18.18% | 3910500 | 9.092% | 19552500.3637 |  | 79084097 | 79084097 | bar: 2025 Q1 to 2029 Q2
| College- Unallocated |  | 2424 |  |  |  | 0 | 0 | -6065826 | -6065826 | [7 empty] | -6065826 |  | -6065826
| College- Unallocated - CM fees unallocated |  | 2424 |  |  |  |  | 0
| Infrastructure |  | 2423 |  |  |  | 11430172 | 12076197
| Infrastructure – Unallocated |  | " |  |  |  |  | 0 | 234234 | 232750 | [7 empty] | 234234 |  | 234234
| Infrastructure CM Fee |  | " |  |  |  |  | 0 | 2514253 | [8 empty] | 2514253 |  | 2514253
| GonLED |  | 2423-03 |  | Complete |  | 0 | 0 | 574308 | 574308 | [7 empty] | 574308 |  | 574308
| Elevator Modernization: Tower and Bldg E Elevators |  | 2423-01 | yes | AM | Mod | 0 | 0 | 1999895 | 1362747 | 149090 | 10.94% |  |  | 326973 | 23.99% | 476063.1094 | 1999895 |  | 1982045 |  | 17850
| Garland Roofing Replacements |  | 2423-02 | yes | Zeb | Mod | 0 | 0 | 3839393 | 3412794 | 341279 | 10% |  |  |  |  | 341279.1 | 3839393 |  | 3839393
| Air Units Modernization |  | 2423-04 | [5 empty] | 0 | [10 empty] | 0
| Elevator Modernization: Kone | 2423.04 | 2423-10 | yes | Zeb | Mod | 0 | 0 | 856990 | 736696 | 72782 | 9.88% |  |  | 47512 | 6.449% | 120294.0988 | 856990 |  | 856990
| BMS System: ESI | 2423.07 | 2423-24 | no |  | Mod | 0 | 0 | 72540 | 72540 | [7 empty] | 72540 |  | 72540
| (1) Fab Lab Relocation |  | 2423-08 | yes | Zeb | Mod | 0 | 0 | 1904443 | 1371035 | 48068 | 3.506% | 16450 | 1.2% | 1595 | 0.1163% | 66113.0471 | 1904443 |  | 1901275 |  | 3168
| (2) Campus Wide Electrical Upgrade Phase 2 |  | 2423-09 | no | TBD | Mod | 0 | 0
| (3) Student Center - Interim Improvements | 2423.1 | 2423-21 | yes | AG | Mod | 0 | 0 | 4959454.09 | 4000000 | 400000 | 10% |  |  | 144500 | 3.612% | 544500.1 | 4959454.09 |  | 4959454.09
| (4) New Compressor/Hoses at Building E |  | 2423-11 | no | LR/SD | Mod | 0 | 0 | 50000 | 50000 | [7 empty] | 50000 |  | 50000
| (5) Tie downs on Tower Roof - Window Washing |  | 2423-12 | no |  | Mod |  | 0
| Baseball Field |  | 2423-13 | yes | Complete |  | 0 | 0 | 883995 | 883995 | [7 empty] | 883995 |  | 883995
| (7) New Gym Floor and Bleachers |  | 2423-14 | no |  | Mod | 0 | 0 | 682130 | 682130 | [7 empty] | 682130 |  | 682130
| EV Charging Station |  | 2423-15 | no | SD/Zeb | Mod | 0 | 0 | 265050 | 265050 | [7 empty] | 265050 |  | 265050
| Forum Women's Restroom Improvements |  | 2423-16 | yes | Complete | Mod | 0 | 0 | 27914 | 27914 | [7 empty] | 27914 |  | 27914
| Welding Exhaust Equipt Anchorage & Storage |  | 2423-17 | yes | Zeb | Mod | 0 | 0 | 16157 | [8 empty] | 16157 |  | 16157
| Kiln Room AC 138 |  | 2423-18 | no | ZB | Mod | 0 | 0 | 96720 | 96720 | [7 empty] | 96720 |  | 96720
| Retro Commissioning |  | 2423-19 | no |  | Mod | 0 | 0 | 1699450 | 1699450 | [7 empty] | 1699450 |  | 1699450
| Emergency Infrastructure |  | 2423-20 | no |  | Mod | 0 | 0 | 1650000 | 1649960 | [7 empty] | 1650000 |  | 964031 |  | 685969
| Student Center Kitchen Elevator | 2423.21 | 2423-07 |  | Complete |  | 0 | 0 | 154845 | 154844.5 | [7 empty] | 154845 |  | 154845
| (6) Football Field |  | 2423-22 | yes | BC | Mod | 0 | 0 | 1489655 | 1481255 | [7 empty] | 1489655 |  | 74063 |  | 1415592
| HVAC -Chiller |  | 2423-23 | yes |  |  | 0 | 0 | 649530 | 649530 | [7 empty] | 649530 |  | 649530
| Bistro Kitchen |  | 2423-25 |  | Complete |  | 0 | 0 | 19480 | 19480 | [7 empty] | 19480 |  | 19480
| Electrical Power, Lighting and Security Repairs |  | 2423-26 | yes | MT |  |  |  | 200000 | 200000 | [7 empty] | 200000 |  | 200000
| Legacy Laney Campus Modernizations |  | 2314 | no |  | Mod | 0 | 0 | 842678 | [8 empty] | 842678 |  | 406916 |  | 435762
| Laney ADA Modernization |  | 2348-01 | no | BC/Zeb | Mod | 0 | 4546654 | 3183547 | 2137697 | [7 empty] | 3183547 |  |  |  | 3183547
| AC Paving Rehabilitation |  | 2348 | yes | Complete | Mod | 0 | 13634 | 299150 | 228569 | [7 empty] | 299150 |  |  |  | 299150
| Laney BEST Center |  | 2437 | yes | AM | Mod | 0 | 156518 | 109047 | 43068 | [7 empty] | 109047 |  | 15006 |  | 94041
| Laney Leak Remediation (Phase 3) |  | 2465 | yes | Complete | Mod | 0 | 1784970 | 3556903 | 3280537 | [7 empty] | 3556903 |  | 9450 |  | 3547453
| Information Technology |  | 2415 | no |  | IT | 5700000 | 5700000 | 5700000 | [8 empty] | 5700000 |  | 5700000
| Library Equipment and Books (based on 2022 adopted BAM) |  | 2378-05
| Laney College Subtotal | [5 empty] | 374606280 | 381754081 | 321995592.09 | 223533670.5 | 21829083 |  | 8817450 |  | 10018482 |  | 40665016.3072 | 242911495.09 | 79084097 | 264856127.09 | 32416000 | 24723465
Merritt College
| Child Development Center - DBB |  | 2425 | yes | VV | New | 27429210 | 27429210 | 37892593 | 27145922 | 2500000 | 9.209% |  |  |  |  | 2500000 | 37892593 |  | 27669845 | 6128000 | 4094748 | bar: 2020 Q1 to 2025 Q3
| Horticulture Building - DBB |  | 2463 | yes | MZ | New | 34872971 | 34872971 | 40583601 | 25532957 | 1945158 | 7.618% |  |  | 5901790 | 23.11% | 7846948 | 40583601 |  | 30083021 | 9789000 | 711580 | bar: 2020 Q2 to 2025 Q1
| Science/Allied Health - TI Buildout - DBB |  | 2353 | yes | JV | Mod | 8343850 | 8343850 | 8545787 | 5587030 | 581925 | 10.42% | 344946 | 6.174% | 489183 | 8.756% | 1416054 | 8545787 |  | 8545787 | bar: 2022 Q2 to 2025 Q2
| Barbara Lee Modernization |  | 2353-01 | yes | BC | Mod | 0 |  | 3080001 | 2000000 | 283941 | 14.2% | 218026 | 10.9% | 110000 | 5.5% | 611967 | 3080001 |  | 3080001
| Campus Wide Modernization |  | 2507 |  |  |  | 0 |  | 4908497 | 4908497 | [7 empty] | 4908497 |  | 4908497
| Campus Wide Mod - Keyless Entry |  | 2507-01 |  | BC |  | 0 |  | 91503 | [8 empty] | 91503 |  | 91503
0 | bar: 2023 Q3 to 2026 Q4
| Locker Room/Gym - DBB |  | 2500 | no | on hold | Mod | 48255645 | 48255645 | 23451874.2262 | 11001874 | 2475000 | 22.5% | 2475000 | 22.5% | 1237500 | 11.25% | 6187500 |  | 23451874.2262 | 23451874.2262 | bar: 2026 Q3 to 2029 Q4
0 | bar: 2023 Q3 to 2026 Q4
| Renovate Building D - DBB |  | 2501 | no |  | Mod | 64830273 | 64830273 | 24927287.6346 | 7583635 | 3397185 | 44.8% | 3397185 | 44.8% | 1698593 | 22.4% | 8492963 |  | 24927287.6346 | 24927287.6346 | bar: 2026 Q3 to 2029 Q4
0
| Demolish Building A - DBB |  | 2502 | no |  | Mod | 3335000 | 3335000
| College- Unallocated |  | 2428 |  |  |  | 0 |  | 990321 | 990321 | [7 empty] | 990321 |  | 990321
| College Unallocated - CM Fees for future projects |  | 2428 | [5 empty] | 1475414 | [8 empty] | 1475414 |  | 1475414
| Infrastructure |  | 2355 |  |  |  | 10830000 | 10830000
| Infrastructure – Unallocated |  | " |  |  | Mod |  |  | 5171634 | 5171634 | [7 empty] | 5171634 |  | 5171634
| Infrastructure- CM Fees |  | " |  |  | Mod |  |  | 1191237 | [8 empty] | 1191237 |  | 1136169 |  | 55068
| Infrrastructure - Retro Commissioning Reserve | [7 empty] | 0 | [8 empty] | 0 |  | 0
| Infrastructure - Sub Stat B, D and Generator-High Priority | [7 empty] | 0 | [8 empty] | 0 |  | 0
| Boiler Inspections |  | 2355-02 | yes | BC-Complete | Mod | 0 |  | 23722 | 23722 | [7 empty] | 23722 |  | 23722
| Training Room Door Replacement- Room F105 |  | 2355.03 | yes | Complete | Mod
| Elec Power - 12 KV Sub Stn C Inspection + Replacement |  | 2355-04 | yes | VV | Mod | 0 |  | 3500000 | 2621740 | 261700 | 9.982% |  |  | 256260 | 9.774% | 517960 | 3500000 |  | 3500000 | bar: 2022 Q2 to 2025 Q3
| Elec Power- Replacement 12KV Load Switch #6 |  | 2355-05 | yes | Complete | Mod | 0 |  | 44836 | 44836 | [7 empty] | 44836 |  | 44836
| Building S Wall Finish Replacement East Wing |  | 2355-06 | yes | Complete | Mod | 0 |  | 14836 | 14836 | [7 empty] | 14836 |  | 14836
| Building D Heating Closed Loop Plumbing Replacement |  | 2355-07 | yes | Complete | Mod | 0 |  | 111337 | 109744 | [7 empty] | 111337 |  | 111337
| Elevator Modernization |  | 2355-08 | yes | BC | Mod | 0 |  | 1649327 | 1423019 | 137378 | 9.654% |  |  | 68930 | 4.844% | 206308 | 1649327 |  | 1649327
| Gym Building F Sewer Inspection |  | 2355-09 | yes | Complete | Mod | 0 |  | 11513 | 11513 | [7 empty] | 11513 |  | 11513
| CDC Heating Issues- A |  | 2355-10 | no | Complete | Mod | 0 |  | 3448 | 3448 | [7 empty] | 3448 |  | 3448
| CDC Heating Issues- Equipment-B |  | 2355-11 | yes | Complete | Mod | 0 |  | 28544 | 28544 | [7 empty] | 28544 |  | 28544
| Plumbing Bndl #3C Bldg A,Q & R |  | 2355-12 | yes | Complete | Mod | 0 |  | 21900 | 21900 | [7 empty] | 21900 |  | 21900
| Roofing Maintenance and Repair |  | 2355-13 | yes | BC | Mod | 0 |  | 89463 | 89463 | [6 empty] | 0 | 89463 |  | 89463
| Campus Wide BMS Issues- Delta Controls |  | 2355-14 | yes | Complete | Mod | 0 |  | 23950 | 23950 | [7 empty] | 23950 |  | 23950
| Building E Boiler Equipment Replacement |  | 2355-16 | yes | Complete | Mod | 0 |  | 13767 | 13767 | [7 empty] | 13767 |  | 13767
| Bid Bundle 4A Doors |  | 2355-17 | yes | Complete | Mod | 0 |  | 27809 | 27809 | [7 empty] | 27809 |  | 27809
| HVAC Bundle 2E Building S and Q |  | 2355-18 | yes | Complete | Mod | 0 |  | 22103 | 22103 | [7 empty] | 22103 |  | 22103
| Gym Scoreboard |  | 2355-20 | yes | Complete | Mod | 0 |  | 58500 | 58500 | [7 empty] | 58500 |  | 58500
| Temp Fence |  | 2355-21 | yes | BC | Mod | 0 |  | 92946 | 92946 | [6 empty] | 0 | 92946 |  | 92946
| Water Infiltration at Vault B |  | 2355-22 | yes | Complete | Mod | 0 |  | 2976 | 2976 | [7 empty] | 2976 |  | 2976
| ADA Project based on 2016 MIG Report |  | 2355-24 | yes | JV | Mod | 0 |  | 3495244 | 2416118 | 241615 | 10% |  |  | 41717 | 1.727% | 283332 | 3495244 |  | 3495244 | bar: 2022 Q2 to 2024 Q4
| Building D Gas Shut Off Valve Replacement |  | 2355-25 | yes | BC-Complete | Mod | 0 |  | 59999 | 59999 | [7 empty] | 59999 |  | 59999
| MPOE-D160 |  | 2355-26 | yes | Complete | Mod | 0 |  | 15000 | 15000 | [7 empty] | 15000 |  | 15000
| MC IDF Cooling Issues Campus Wide |  | 2355-27 | yes | BC | Mod | 0 |  | 24827 | 24827 | [7 empty] | 24827 |  | 24827
| Retro Commissioning |  | 2355-28 | yes | MZ | Mod | 0 |  | 8731444 | 6244316 | 624432 | 10% | 166602 | 2.668% | 312216 | 5% | 1103250 | 8731444 |  | 8731444 | bar: 2023 Q3 to 2025 Q4
| Sub Stat B, D and Generator-High Priority |  |  |  | MZ
| Plumbing Building F Boiler Room Pump #4 Rebuild |  | 2355-29 | yes | BC | Mod | 0 |  | 30000 | 25000 | 5000 | 20% |  |  |  |  | 5000 | 30000 |  | 30000
| HVAC Modernization Building F & R Part 2 |  | 2355-30 | yes | BC | Mod | 0 |  | 170500 | 125000 | 25000 | 20% |  |  | 15500 | 12.4% | 40500 | 170500 |  | 170500
| Soccer Field |  | 2355-31 | yes | BC |  | 0 |  | 1018779 | 1018779 | [7 empty] | 1018779 |  | 1018779
| Emergency Electrical Repair Work |  | 2355-32 | no | BC |  | 0 |  | 481349 | 442282 | [7 empty] | 481349 |  | 481349
| Training Room F105 |  | 2355-33 | [5 empty] | 164010 | 149100 | 14910 | [6 empty] | 164010 |  | 164010
| Fence at Parking Lot B |  | 2503 | no | BC | New | 2500000 | 2500000 | 2500000 | 1743750 | 125000 | 7.168% | 125000 | 7.168% |  |  | 250000 | 2500000 |  | 2500000
| Merritt Building Modernizations |  | 2372 | no | Complete | Mod | 0 | 8198 | 8197 | 8197 | [7 empty] | 8197 |  |  |  | 8197
| Information Technology |  | 2364/2416 | no | BC | IT | 2850000 | 2850000 | 2850000 | [8 empty] | 1425000 | 1425000 | 2850000
| Library Equipment and Books (based on 2022 adopted BAM) |  | 2378-06
2022
| Merritt College Subtotal | [5 empty] | 203246949 | 203255147 | 177600075.8608 | 106829054 | 12618244 |  | 6726759 |  | 10131689 |  | 29461782 | 127795914 | 49804161.8608 | 156813482.8608 | 15917000 | 4869593
Districtwide
| Administrative Complex Repairs |  | 2321 | no |  | Mod | 4361000 | 4361000 | 329765 | 304190 | [7 empty] | 329765 |  | 329765
| Chancellor's Restroom |  | 2321-01 |  |  |  | 0 |  | 86900 | 55000 | 5500 | 10% |  |  | 5500 | 10% |  | 86900 |  | 86900
| Roof Repair |  | 2321-02 |  | complete |  | 0 |  | 1647488 | 1647488 | [7 empty] | 1647488 |  | 977995 |  | 669493
| IT Chiller |  | 2321-03 | yes |  |  | 0 |  | 300000 | 250000 | 30000 | 12% | [5 empty] | 300000 |  | 300000
| Sherriff's Locker Room Restroom |  | 2321-04 |  |  |  | 0 |  | 11975 | 3350 | [7 empty] | 11975 |  | 11975
| DGS Remodel | [6 empty] | 0 | 0 | [8 empty] | 0 |  | 0
| Flooring |  | 2321-05 | [5 empty] | 271000 | 271000 | [7 empty] | 271000 |  | 271000
| Fire Alarm System Modernization |  | 2321-06 | [5 empty] | 1449860 | 1106000 | [7 empty] | 1449860 |  | 1449860
| Information Technology (Includes Security Cameras Phase 2-$2,163,392)) |  | 2446 | Security Cameras only |  | IT | 10000000 | 12253799 | 10590620 | [8 empty] | 10590620 |  | 10590620
| Blue Phone Installation - Phase 2 |  | 2429 | no | BC | New | 3511055 | 3511055 | 3511055 | 1964571 | 275092 | 14% |  |  | 112143 | 5.708% | 275092 | 3511055 |  | 3371990 |  | 139065
| Chromebook Purchase |  | 2446 |  | complete | IT | 3500000 | 3500000 | 3053618 | [8 empty] | 3053618 |  | 3053618
| FF&E & IT |  | 2418 |  | complete |  | 0 |  | 119155 | [8 empty] | 119155 |  | 45000 |  | 74155
| Districtwide Elevator Upgrades |  | 2325 | no |  | Mod | 0 | 634777 | 634777 | 506730 | [7 empty] | 634777 |  | 574179 |  | 60598
| Districtwide Lighting Project |  | 2326 | [5 empty] | 19400 | 19400 | [7 empty] | 19400 |  | 19400
| Districtwide Security |  | 2328 | no | BC-Cameras, xx Gates | Prog | 0 | 78717 | 74732 | [8 empty] | 74732 |  |  |  | 74732
| Districtwide Fire Panel Upgrades |  | 2402 | no | Complete | Mod | 0 | 89416 | 318842 | 314892 | [7 empty] | 318842 |  |  |  | 318842
| Districtwide Planning |  | 2407 | no |  | Prog | 0 | 518974 | 219424 | 81298 | [7 empty] | 219424 |  |  |  | 219424
| 860 Atlantic (Genomics) - DBB |  | 2356 | no | Complete | Mod |  | 0 | 0 | [8 empty] | 0 |  |  |  | 0
| 860 Atlantic HVAC Upgrades |  | 2408 | yes | Complete | Mod |  | 0 | 0 | [8 empty] | 0 |  |  |  | 0
| Districtwide Signage |  | 2334 | no | Complete | Mod | 0 |  | 13634 | [8 empty] | 13634 |  |  |  | 13634
| Program Contingency (5% + Interest) |  | 2432 |  |  | Prog | 40000000 | 40000000 | 40000000 |  | 40000000 | [5 empty] | 40000000 | 40000000 |  | 40000000
| Unallocated Contingency (Measure A Reconciliation) |  | xxxx |  |  | Prog |  |  | 0 | [8 empty] | 0 |  | 0 |  | 0
| Program Management |  | 2300 |  |  | Prog | 20000000 | 20000000 | 20000000 | [8 empty] | 20000000 |  | 19481378 |  | 518622
| District Bond Management |  | 2300-02 |  |  | Prog | 14000000 | 14000000 | 14000000 | [8 empty] | 14000000 |  | 8308206 |  | 5691794
| Legal |  | 2300-03 |  |  | Prog | 3500000 | 3500000 | 3500000 | [8 empty] | 3500000 |  | 2709306 |  | 790694
| Auditing |  | 2300-04 |  |  | Prog | 250000 | 250000 | 250000 | [8 empty] | 250000 |  | 250000
| Sustainability Plan Implementation |  | 2300-01 |  |  | New
| Library Equipment and Books |  | 2378 |  |  |  | 7000000 | 7000000 | 7000000 | [8 empty] | 7000000 |  | 7000000
| Districtwide Unallocated |  | 7777 |  |  |  | 0 |  | 3779181 | 3779181 | [7 empty] | 3779181 |  | 3779181
0
| 2021 | [7 empty] | 0
| Districtwide Subtotal | [5 empty] | 106122055 | 109697738 | 111181426 | 10303100 | 40310592 |  |  |  | 117643 |  | 40275092 | 111181426 | 0 | 102610373 | 0 | 8571053
Grand Total | [6 empty] | 1000865000 | 1025992000 | 953180510.9412 | 587304793.5 | 85654634 |  | 23087871.5 |  | 30766440 |  | 139340893.8072 | 722468178.6425 | 230712332.2987 | 800000001.9412 | 77144000 | 76036509
1 Type of Project: New Construction (New); Modernization (Mod); Information Technology (IT); Program-wide (Prog)
2 Total Project Cost Estimate: Total Capital Costs, including Hard Costs for Construction Building/Interiors and Soft Costs for Development Fees/Consultants. Typical Ratio is 70% Hard to 30% Soft Costs.
3 FPP - Final Project Proposal: Design Funded in 19/20 and Construction Funded in FY 21/22 - FY 22/23
IPP - Initial Project Proposal: Future Funding Proposal for FY 23/24
4 Allocation per Peralta Finance Budget sent to PMO on 10/15/20, with project adjustments to reflect actuals holding College Measure A Allocation.
Previous BSP Before Laney Deferral of State Funding for Projects
Variance to Current
1 Type of Project: New Construction (New); Modernization (Mod); Information Technology (IT); Program-wide (Prog)
2 Total Project Cost Estimate: Total Capital Costs, including Hard Costs for Construction Building/Interiors and Soft Costs for Development Fees/Consultants. Typical Ratio is 70% Hard to 30% Soft Costs.
3 FPP - Final Project Proposal: Design Funded in 19/20 and Construction Funded in FY 21/22 - FY 22/23; IPP - Initial Project Proposal: Future Funding Proposal for FY 23/24
4 Allocation per Peralta Finance Budget sent to PMO on 10/15/20, with project adjustments to reflect actuals while holding each overall College Measure A Allocation.
*** Per current approved DCA. This value will be reduced once Roebbelen submits revised DCA because Roofing scope is going to be deleted (included in Infrastructure) and Freezer Replacement will be deleted (on hold).
Library Equipment and Books (Moved to campuses)